## Defect
| Title | Screen | Pre-condition | Steps | Expected Results | Actual results | Priority | Serverity | Date | Owner | TC'ID | Build | System | Assign To | Status | Evident (Hình ảnh lỗi)
DF_1 | The Product Type module is difficult to use and displays incorrectly when accessed via the mobile web | Product Type | Administrator account logged in on the mobile web, with existing product type data displayed | 1. Open a mobile browser (Chrome or Safari). 2. Log in to the PRS system. 3. Select the “Product Type” module. | 1. The application opens correctly on the mobile browser. 2. The login page fits the screen, no layout overflow. 3. The “Product Type” page displays fully with proper alignment. | 2. When accessing the "Sales Dashboard" page on the mobile web, the layout is broken. The title is split into multiple lines, and the “Last updated” text and “Refresh” button are misaligned compared to the expected design. 3. The “Add via Excel” button is difficult to use — it only displays as “Add b.” When a checkbox is selected, the “Delete All” button overlaps and hides the “Add via Excel” button. Only part of the “Add New” button is visible, and pagination is not displayed. | Normal | Low | 31/10/2025 | Lê Nguyễn Thành Đạt | TC_LSP_018 |  |  |  |  | Ảnh lỗi
DF_2 | Searching by employee name does not work | Product Type | Logged in as admin | 1. Log in to the PRS software. 2. Go to the Employee module. 3. Enter “Phan Nhi” into the search box. 4. Press Enter | 1. Go to the software’s homepage. 2. Employee list screen displays correctly 3. “Phan Nhi” is displayed in the search bar.x 4. Employee “Phan Nhi” is displayed in the list. | 1. The result matches the expected results. 2. The result matches the expected results. 3. The result matches the expected results. 4. The list does not display the employee “Phan Nhi” | High | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_3 | The Email field allows invalid formats to be entered | Employee | Logged in as admin | 1. Log in to the PRS software. 2. Go to the Employee module. 3. Click button "Add Employee" 4. Enter an incorrectly formatted email, e.g., lntd1803@Dat.com , into the Email field. | 1. Go to the software’s homepage. 2. Employee list screen displays correctly 3. Display the Add Employee screen. 4. A red error message appears below the textbox stating: "Invalid email address" | 1. The result matches the expected results. 2. The result matches the expected results. 3. The result matches the expected results. 4. An error message is displayed only when the “@” symbol is missing; however, the system does not show an error for invalid domain parts after “@”. | High | High | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_4 | The Start Date field should not allow selecting a date later than the current date. | Employee | Logged in as admin | 1. Log in to the PRS software. 2. Go to the Employee module. 3. Click button "Add Employee" 4. Select a date later than the current date in the Start Date date picker. | 1. Go to the software’s homepage. 2. Employee list screen displays correctly 3. Display the Add Employee screen. 4. There is a red notice below the DatePicker that says: Invalid start date | 1. The result matches the expected results. 2. The result matches the expected results. 3. The result matches the expected results. 4. A date later than the current date can be selected without displaying an error message. | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_5 | The Start Date field should not allow selecting a date later than the current date. | Employee | Logged in as admin | 1. Log in to the PRS software. 2. Go to the Employee module. 3. Click button "Edit Employee" 4. Select a date later than the current date in the Start Date date picker. | 1. Go to the software’s homepage. 2. Employee list screen displays correctly 3. Display the Edit Employee screen. 4. There is a red notice below the DatePicker that says: Invalid start date | 1. The result matches the expected results. 2. The result matches the expected results. 3. The result matches the expected results. 4. A date later than the current date can be selected without displaying an error message. | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_6 | Enter incorrectly formatted data into the Phone Number field | Employee | Logged in as admin | 1. Log in to the PRS software. 2. Go to the Employee module. 3. Click button "Add Employee" 4. Enter “1232221312,” which is an invalid format, into the Phone Number field. | 1. Go to the software’s homepage. 2. Employee list screen displays correctly 3. Display the Add Employee screen. 4. A red error message appears below the textbox: “Invalid phone number.” | 1. The result matches the expected results. 2. The result matches the expected results. 3. The result matches the expected results. 4. No error message appears, and the data is saved successfully. | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_7 | The Email field allows invalid formats to be entered (Edit Employee) | Edit Employee | Logged in as admin | 1. Log in to the PRS software. 2. Go to the Employee module. 3. Click button "Edit Employee" 4. Enter an incorrectly formatted email, e.g.,21d2á1ds2a@s.com , into the Email field. | 1. Go to the software’s homepage. 2. Employee list screen displays correctly 3. Display the Add Employee screen. 4. A red error message appears below the textbox stating: "Invalid email address" | 1. The result matches the expected results. 2. The result matches the expected results. 3. The result matches the expected results. 4. An error message is displayed only when the “@” symbol is missing; however, the system does not show an error for invalid domain parts after “@”. | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_8 | Enter incorrectly formatted data into the Phone Number field (Edit Employee) | Edit Employee | Logged in as admin | 1. Log in to the PRS software. 2. Go to the Employee module. 3. Click button "Edit Employee" 4. Enter “1234556,” which is an invalid format, into the Phone Number field. | 1. Go to the software’s homepage. 2. Employee list screen displays correctly 3. Display the Add Employee screen. 4. A red error message appears below the textbox: “Invalid phone number.” | 1. The result matches the expected results. 2. The result matches the expected results. 3. The result matches the expected results. 4. No error message appears, and the data is saved successfully. | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_9 | Faulty dropdown buttons are displayed on the mobile interface (not showing enough/obscured) | Employee | Administrator account logged in on the mobile web | 1. Open a mobile browser (Chrome or Safari). 2. Log in to the PRS system. 3. Select the “Employee” module. 4. Check the dropdown buttons. | 1. The application opens correctly on the mobile browser. 2. The login page fits the screen, no layout overflow. 3. The “Employee” page displays fully with proper alignment. 4. The dropdown menu is fully visible within the mobile screen viewport. • All options in the dropdown can be selected, and the interface does not overflow or misalign. • The layout is responsive to the screen size. | 1. The result matches the expected results. 2. The result matches the expected results. 3. The result matches the expected results. 4. The dropdown menu is not fully visible or is partially obscured. • In some cases, it is impossible to select any option from the menu (hidden outside the viewport). • The table layout is misaligned, and column dividers are uneven. | High | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_10 | Error in displaying employee information on the mobile interface - text is overflowing and character breaks are not in the right place | View Detail Employee | Administrator account logged in on the mobile web | 1. Open a mobile browser (Chrome or Safari). 2. Log in to the PRS system. 3. Select the “Employee” module. 4. Click "View Detail Employee" one Employee 5. Observe the display of the employee’s personal information. | 1. The application opens correctly on the mobile browser. 2. The login page fits the screen, no layout overflow. 3. The “Employee” page displays fully with proper alignment. 4. Display the Employee Information Details screen. 5. Text values are displayed completely without character truncation. • The layout automatically adjusts to the screen size (responsive). • Padding, spacing, and layout are clear and easy to read on mobile screens. • Information in the two columns is separated and not overlapping. | 1. The result matches the expected results. 2. The result matches the expected results. 3. The result matches the expected results. 4. The result matches the expected results. 5. Characters in the employee’s name, email, and phone number are truncated (e.g., á51d5ád1s5a1f5...). • Text overflows the display area or wraps incorrectly. • The “Personal Information” and “Work Information” columns are too narrow, causing text to overlap in some sections. • There is insufficient spacing or padding between elements when displayed on mobile. | High | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_11 | The employee list interface does not display properly on mobile devices | Employee | Administrator account logged in on the mobile web | 1. Open a mobile browser (Chrome or Safari). 2. Log in to the PRS system. 3. Select the “Employee” module. | 1. The application opens correctly on the mobile browser. 2. The login page fits the screen, no layout overflow. 3. Text values are displayed completely without character truncation. • The layout automatically adjusts to the screen size (responsive). • Information in the two columns is separated and not overlapping. | 1. The result matches the expected results. 2. The result matches the expected results. 3. The table display does not fit the mobile screen size. Users must scroll horizontally to view all data. | High | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_12 | Provider names that are longer than 200 characters | Add Supplier | Logged in as admin | 1. Log in to the PRS software. 2. Go to the Supplier module. 3. Click button "Add Supplier" 4. Enter 202 character string “abcdefghijklmnopqrstuvwxyzABCDEFGHIJKLMNOPQRSTUVWXYZ0123456789abcdefghijklmnopqrstuvwxyzABCDEFGHIJKLMNOPQRSTUVWXYZ0123456789abcdefghijklmnopqrstuvwxyzABCDEFGHIJKLMNOPQRSTUVWXYZ0123456789abcddádasd” which is an invalid format, into the Name Supplier field. | 1. Go to the software’s homepage. 2. Supplier list screen displays correctly 3. Display the Add Supplier screen. 4. A red error message appears below the textbox: “The supplier name must have a maximum of 200 characters.” | 1. The result matches the expected results. 2. The result matches the expected results. 3. The result matches the expected results. 4. No message appears, and the data can be saved successfully. | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_13 | Incorrectly formatted Provider Email field | Add Supplier | Logged in as admin | 1. Log in to the PRS software. 2. Go to the Supplier module. 3. Click button "Add Supplier" 4. Enter “lntd@g.com” which is an invalid format, into the Email field. | 1. Go to the software’s homepage. 2. Supplier list screen displays correctly 3. Display the Add Supplier screen. 4. A red error message appears below the textbox: “Invalid email address” | 1. The result matches the expected results. 2. The result matches the expected results. 3. The result matches the expected results. 4. An error message is displayed only when the “@” symbol is missing; however, the system does not show an error for invalid domain parts after “@”. | High | High | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_14 | Incorrectly formatted Provider Phone Number field | Add Supplier | Logged in as admin | 1. Log in to the PRS software. 2. Go to the Supplier module. 3. Click button "Add Supplier" 4. Enter “1234567” which is an invalid format, into the Phone number field. | 1. Go to the software’s homepage. 2. Supplier list screen displays correctly 3. Display the Add Supplier screen. 4. A red error message appears below the textbox: “Phone number” | 1. The result matches the expected results. 2. The result matches the expected results. 3. The result matches the expected results. 4. No error message appears below the textbox. However, when the phone number starts with “0,” the validation works correctly as described; when the number does not start with “0,” the validation fails. | High | High | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_15 | Misformatted provider mobile field | Add Supplier | Logged in as admin | 1. Log in to the PRS software. 2. Go to the Supplier module. 3. Click button "Add Supplier" 4. Enter “1234567” which is an invalid format, into the Mobile number field. | 1. Go to the software’s homepage. 2. Supplier list screen displays correctly 3. Display the Add Supplier screen. 4. A red error message appears below the textbox: “Mobile number” | 1. The result matches the expected results. 2. The result matches the expected results. 3. The result matches the expected results. 4. No error message appears below the textbox. However, when the phone number starts with “0,” the validation works correctly as described; when the number does not start with “0,” the validation fails. | High | High | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_16 | Incorrectly formatted Contact Email field | Add Supplier | Logged in as admin | 1. Log in to the PRS software. 2. Go to the Supplier module. 3. Click button "Add Supplier" 4. Enter “lntd@g.com” which is an invalid format, into the Email Contact person field. | 1. Go to the software’s homepage. 2. Supplier list screen displays correctly 3. Display the Add Supplier screen. 4. A red error message appears below the textbox: “Invalid email Contact person” | 1. The result matches the expected results. 2. The result matches the expected results. 3. The result matches the expected results. 4. An error message is displayed only when the “@” symbol is missing; however, the system does not show an error for invalid domain parts after “@”. | High | High | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_17 | Incorrectly formatted Contact Phone Number field | Add Supplier | Logged in as admin | 1. Log in to the PRS software. 2. Go to the Supplier module. 3. Click button "Add Supplier" 4. Enter “1234567” which is an invalid format, into the Phone number Contact person field. | 1. Go to the software’s homepage. 2. Supplier list screen displays correctly 3. Display the Add Supplier screen. 4. A red error message appears below the textbox: “Phone number Contact person” | 1. The result matches the expected results. 2. The result matches the expected results. 3. The result matches the expected results. 4. No error message appears below the textbox. However, when the phone number starts with “0,” the validation works correctly as described; when the number does not start with “0,” the validation fails. | High | High | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_18 | NV Sales History page displays Debug Info | Employee sales history | Logged in as admin | 1. Log in to the PRS software. 2. Go to the Employee sales history module. 3. Observe the data statistics display area. | 1. Go to the software’s homepage. 2. Employee sales history list screen displays correctly 3. No debug information or internal code is displayed on the user interface. | 1. The result matches the expected results. 2. The result matches the expected results. 3. The screen displays debug code: Debug Info: Orders Data Length: 0 Loading: No Statistics: {"totalOrders":0,"totalRevenue":0,"avgOrderValue":0,"completedOrders":0} | High | High | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_19 | The "NV Sales History" page displays a debug code and fails to load the order list | Employee sales history | Logged in as admin | 1. Log in to the PRS software. 2. Go to the Employee sales history module. 3. Scroll to the “All Orders” section. | 1. Go to the software’s homepage. 2. Employee sales history list screen displays correctly 3. If there are no orders, display “No order data available.” If orders exist, display the order list without exposing any code on the page. | 1. The result matches the expected results. 2. The result matches the expected results. 3. The page displays debug code: Table Data Debug: Data Source Length: 0 Loading State: false Columns Length: 8 | High | High | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_20 | Module Supplier without roller bar | Supplier | Logged in as admin | 1. Log in to the PRS software. 2. Go to the Supplier module. 3. Check the scroll bar. | 1. Go to the software’s homepage. 2. Supplier list screen displays correctly 3. The scroll bar is functioning properly. | 1. The result matches the expected results. 2. The result matches the expected results. 3. The scroll bar is not functioning. | High | High | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_21 | Enter data in the Raw field of the recipe edit causing the page crash – displays the error "l.toLowerCase is not a function" | Crafting Recipe | Logged in as admin | 1. Log in to the PRS software. 2. Go to the Crafting Recipe module. 3. Select a random recipe 4. Click Edit 5. Enter Apple (1kg) into the ingredients dropdown | 1. Go to the software’s homepage. 2. Crafting Recipe list screen displays correctly 4. Display the recipe editing screen 5. Do not show any alert or throw an error; if it does not exist, leave the ingredient absent in the dropdown | 1. The result matches the expected results. 2. The result matches the expected results. 3. The result matches the expected results. 4. The result matches the expected results. 5. The page crashes completely. Display the error message: Unexpected Application Error! l.toLowerCase is not a function At the bottom, show the developer debug suggestion: “Provide your own ErrorBoundary or errorElement...” | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_22 | Check for changes or removal of formulas from products | Formulated Products | Logged in as admin | 1. Go to the website 2. Tap the formula product function 3. Choose the formula associated with the product 4. Press the "OK" button 5. Delete the selection formula | 1. Display the website 2. Enter success 3. Choose success 4. Products have been added 5. Delete a formula selection to formula | 1. Display the website 2. Enter success 3. Choose success 4. Products have been added 5. No recipe button removal process | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_23 | Check the total recipe cost | Formulated Products | Logged in as admin | 1. Vào trang web 2. Nhấn vào chức năng sản phẩm công thức 3. Chọn Phân tích chi phí 4. Xem thông tin | 1. Go to the website 2. Tap the formula product function 3. Select Cost Analysis 4. View information | 1. Display the website 2. Product Function Form Display 3. See success 4. Total cost is misrepresented | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_24 | Check the image of the product in the recipe view | Formulated Products | Logged in as admin | 1. Go to the website 2. Tap the formula product function 3. Select View details 4. View Product Images | 1. Display the website 2. Product Function Form Display 3. See success 4. Product pictures appear clear | 1. Display the website 2. Product Function Form Display 3. See success 4. No Product Pictures | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_25 | Check the display of the Unformulated Product message | Formulated Products | Logged in as admin | 1. Go to the website 2. Tap the formula product function 3. Choose a product that doesn't have an associated formula 4. See the interface | 1. Display the website 2. Product Function Form Display 3. Product Show 4. The interface displays the message "The product does not have a formula" | 1. Display the website 2. Product Function Form Display 3. Product Show 4.The interface does not display the message "The product has no formula" | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_26 | Check for duplicate formula associations | Formulated Products | Logged in as admin | 1. Go to the website 2. Tap the formula product function 3. Select the recipe link with the default recipe of "Black Coffee" 4. Select the recipe link as "Black Coffee" | 1. Display the website 2. Product Function Form Display 3. Display the product link form 4. Show duplicate link message | 1. Display the website 2. Product Function Form Display 3. Display the product link form 4. Choose success | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_27 | Check the view details button | Formulated Products | Logged in as admin | 1. Go to the website 2. Tap the formula product function 3. Click to view product details | 1. Display the website 2. Product Function Form Display 3.View success | 1. Display the website 2. Product Function Form Display 3.Displaying unviewable notifications | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_28 | Check the view details button in the "View by recipe" section | Formulated Products | Logged in as admin | 1. Go to the website 2. Tap the formula product function 3. Tap "View by Formula" 4.Click to view details | 1. Display the website 2. Product Function Form Display 3. Display the form "View by recipe" 4.View success | 1. Display the website 2. Product Function Form Display 3. Display the form "View by recipe" 4. Unwatchable | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_29 | Check the display of the interface on the phone | Formulated Products | Logged in as admin | 1. Go to the website 2. Tap the formula product function 3. Tap "View Details" 4. View product price | 1. Display the website 2. Product Function Form Display 3. Display the "View Details" form 4. The cost price is in line with the formula price with the girl formula link | 1. Display the website 2. Product Function Form Display 3. Display the "View Details" form 4. Incorrect cost price | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_30 | Kiểm tra hiển thị giao diện trên điện thoại | Formulated Products | Logged in as admin | 1. Enter the website with your phone 2. See the interface | 1. Display the website 2. Beautiful, user-friendly interface | 1. Display the website 2. The interface is constrained, difficult to access | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_31 | Check import/export product links | Formulated Products | Logged in as admin | 1. Go to the website 2. Tap the formula product function 3. Click the product link 4. See the interface | 1. Successful Website Entry 2. Product Function Form Display 3. Enter the successful product link 4. Show the import/export button | 1. Successful Website Entry 2. Product Function Form Display 3. Enter the successful product link 4. Do not display import/export buttons | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_32 | Check for duplicate warehouse names | Warehouse | Logged in as admin | 1. Go to the website 2. Tap the Warehouse function 3. Add Warehouse 4. Edit a warehouse that matches another warehouse name | 1. Successful Website Entry 2. Display the Warehouse form 3. Add a successful warehouse 4. Warehouse duplicate error message | 1. Successful Website Entry 2. Display the Warehouse form 3. Add a successful warehouse 4. Successful warehouse editing | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_33 | Check the display of the interface on the phone | Warehouse | Logged in as admin | 1. Enter the website with your phone 2. See the interface | 1. Display the website 2. Beautiful, user-friendly interface | 1. Display the website 2. The interface is constrained, difficult to access | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_34 | Inspection doesn't show data in the warehouse | Warehouse | Logged in as admin | 1. Go to the website 2. Tap the Warehouse function 3. Tap your inventory 4. See the interface | 1. Successful Website Entry 2. Display the Warehouse form 3. Display your Warehouse form 4. Data has been added to the warehouse | 1. Successful Website Entry 2. Display the Warehouse form 3. Display your Warehouse form 4. Data not added | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_35 | Check the font | Warehouse | Logged in as admin | 1. Go to the website 2. Click Add inventory 3.Enter the warehouse name and Address 4.Tap more 5. View Warehouse Fonts | 1. Successful Website Entry 2. Display the form to add a warehouse 3.Enter the warehouse name and Address 4. Successfully create a warehouse 5. Easy-to-see warehouse font | 1. Successful Website Entry 2. Display the form to add a warehouse 3.Enter the warehouse name and Address 4. Successfully create a warehouse 5. Overflowing stock fonts | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_36 | Check to Warehouse Name Space | Warehouse | Logged in as admin | 1. Go to the website 2. Click Add inventory 3.Leave warehouse name blank 4.Tap more | 1. Successful Website Entry 2. Display the form to add a warehouse 3. Leave a gap to report an error 4. Inventory creation failed | 1. Successful Website Entry 2. Display the form to add a warehouse 3. Leave the white space successful 4. Successfully create a warehouse | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_37 | Check inventory clearance when inventory is still in stock | Warehouse | Logged in as admin | 1. Go to the website 2. Tap the Warehouse function 3. Click delete inventory when there is still inventory in stock | 1. Successful Website Entry 2. Display the Warehouse function form 3.Deletion failed | 1. Successful Website Entry 2. Display the Warehouse function form 3.Successful deletion | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_38 | Check to address whitespace | Warehouse | Logged in as admin | 1. Go to the website 2. Click Add inventory 3.Leave address space 4.Tap more | 1. Successful Website Entry 2. Display the form to add a warehouse 3. Leave a gap to report an error 4. Inventory creation failed | 1. Successful Website Entry 2. Display the form to add a warehouse 3. Leave the white space successful 4. Successfully create a warehouse | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_39 | Check data when selecting a warehouse | Warehouse | Logged in as admin | 1. Go to the website 2. Tap the Warehouse function 3.Select the desired warehouse 4.View information | 1. Successful Website Entry 2. Display the Warehouse function form 3.Choose success 4.Warehouse data display | 1. Successful Website Entry 2. Display the Warehouse function form 3.Choose success 4. Does not display warehouse data | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_40 | Check the warehouse name limit | Warehouse | Logged in as admin | 1. Go to the website 2. Tap the Warehouse function 3. Select more warehouses 4. Entering the warehouse name is too long | 1. Successful Website Entry 2. Display the form to add a warehouse 3. Display the form to add inventory 4. Display a nomenclature that exceeds the allowed characters | 1. Successful Website Entry 2. Display the form to add a warehouse 3. Display the form to add inventory 4. More Success | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_41 | Check the address limit | Warehouse | Logged in as admin | 1. Go to the website 2. Tap the Warehouse function 3. Select more warehouses 4. Entering the warehouse address is too long | 1. Successful Website Entry 2. Display the form to add a warehouse 3. Display the form to add inventory 4. Display a message to set the address beyond the allowed characters | 1. Successful Website Entry 2. Display the form to add a warehouse 3. Display the form to add inventory 4. More Success | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_42 | Check the display of the interface on the phone | Inventory management | Logged in as admin | 1. Enter the website with your phone 2. See the interface | 1. Display the website 2. Beautiful, user-friendly interface | 1. Display the website 2. The interface is constrained, difficult to access | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_43 | Inventory inspection for non-existent warehouse | Inventory management | Logged in as admin | 1. Go to the website 2. Click Manage Inventory 3. Click Warehouse 4. Select a warehouse that is not in stock 5. Click Warehouse | 1. Successful Website Entry 2. Display the Inventory Management form 3. Display the warehousing form 4. Unable to select non-existent warehouses | 1. Successful Website Entry 2. Display the Inventory Management form 3. Display the warehousing form 4. Choose a warehouse | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_44 | Check for out-of-stock in excess of current inventory | Inventory management | Logged in as admin | 1. Go to the website 2. Click Manage Inventory 3. Press any stock you want 4. Click the "-" icon 5. Enter the current inventory "-1" | 1. Successful Website Entry 2. Display the Inventory Management form 3.Choose success 4. Discharge form display 5. Display negative warehouse import and export message | 1. Successful Website Entry 2. Display the Inventory Management form 3.Choose success 4. Discharge form display 5.Import Successfully | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_45 | Check the outbound font | Inventory management | Logged in as admin | 1. Go to the website 2. Click Manage Inventory 3. Press any stock you want 4. Press Export 5. View the font | 1. Successful Website Entry 2. Display the Inventory Management form 3.Choose success 4. Discharge form display 5. Reasonable font | 1. Successful Website Entry 2. Display the Inventory Management form 3.Choose success 4. Discharge form display 5.Font is overflowing, invalid | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_46 | Checking data at warehousing | Inventory management | Logged in as admin | 1. Go to the website 2. Click Manage Inventory 3. Click the warehouse icon for any warehouse 4.View available data of warehousing | 1. Successful Website Entry 2. Display the Inventory Management form 3. Display the warehousing form 4.Display the warehouse name you want to enter | 1. Successful Website Entry 2. Display the Inventory Management form 3. Display the warehousing form 4. The name of the warehouse is not displayed as you enter the additional warehouse | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_47 | Check the out-of-stock when the unit is different from the product unit | Inventory management | Logged in as admin | 1. Go to the website 2. Click Manage Inventory 3. Select the warehouse whose unit is pice 4. Press Export 5.Enter the unit in liters 6. Press Export | 1. Successful Website Entry 2. Display the Inventory Management form 3.Successful warehouse selection 4. Discharge form display 5. Enter successfully 6. Delivery failed because of the wrong unit | 1. Successful Website Entry 2. Display the Inventory Management form 3.Successful warehouse selection 4. Discharge form display 5. Enter successfully 6. Successful shipment | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_48 | Check inventory quantities | Inventory management | Logged in as admin | 1. Go to the website 2. Click Manage Inventory 3. Select any warehouse 4. Enter the quantity as "1.02" 5. Click Warehouse 6. Select the warehouse you just imported 7. Click the outbound icon 8. Enter the quantity as "1" 9. Click Export 10. Display the interface form | 1. Successful Website Entry 2. Display the Inventory Management form 3.Successful warehouse selection 4.Successful warehouse selection 5.Press success 6.Choose success 7.Press success 8.Import Successfully 9.Press success 10. Display inventory as "0.02" | 1. Successful Website Entry 2. Display the Inventory Management form 3.Successful warehouse selection 4.Successful warehouse selection 5.Press success 6.Choose success 7.Press success 8.Import Successfully 9.Press success 10. Display inventory as "2.220446049250313e-16 pice" | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_49 | Check that the out-of-stock is larger than the current warehouse | Inventory management | Logged in as admin | 1. Go to the website 2. Click Manage Inventory 3. Click on the warehouse with the inventory of "10" 4. Press Export 5. Select "11" | 1. Successful Website Entry 2. Display the Inventory Management form 3.Choose success 4. Discharge form display 5. Display the notice of not being shipped out of stock larger than the current quantity | 1. Successful Website Entry 2. Display the Inventory Management form 3.Choose success 4. Discharge form display 5. Successful shipment | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_50 | Check your warehouse search | Inventory management | Logged in as admin | 1. Go to the website 2. Click Manage Inventory 3. Click search for inventory 4. View the warehouse information you search for | 1. Successful Website Entry 2. Display the Inventory Management form 3. Search for "Nguyen Huu Tien" 4.Display the warehouse name you entered | 1. Successful Website Entry 2. Display the Inventory Management form 3. Search for "Nguyen Huu Tien" 4.No warehouse display | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi
DF_51 | Check the date of the transaction history | Inventory management | Logged in as admin | 1. Go to the website 2. Click Manage Inventory 3. Tap Transaction History 4.Click Date | 1. Successful Website Entry 2. Display the Inventory Management form 3. Display transaction history form 4. Display new trading dates, old trading dates | 1. Successful Website Entry 2. Display the Inventory Management form 3. Display transaction history form 4. Failure to perform the function | Normal | Normal | 31/10/2025 | Lê Nguyễn Thành Đạt | [5 empty] | Ảnh lỗi

## IMG
DF_1
DF_2
DF_3
DF_4
DF_5
DF_6
DF_7
DF_8
DF_9 và DF_11
DF_10
DF_12
DF_13
DF_14
DF_15
DF_16
DF_17
DF_18
DF_19
DF_20
DF_21

## Image
ID | Mô tả
DF_22
DF_23
DF_24
DF_25
DF_26
DF_27
DF_28
DF_29
DF_30
DF_31
DF_32
DF_33
DF_34
DF_35
DF_36
DF_37
DF_38
DF_39
DF_40
DF_41
DF_42
DF_43
DF_44
DF_45
DF_46
DF_47
DF_48
DF_49
DF_50
DF_51